{"text_format":"2","workbook":"xls","n_sheets":4,"sheets":["32M内訳追記","SH対応","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"32M内訳追記","index":0,"n_rows":30,"n_cols":13,"rows_kept":30,"cut":false,"hidden":false,"merged":[[19,1,25,1],[19,2,25,2],[3,5,4,5],[5,5,11,5],[3,2,11,2],[12,2,15,2],[1,5,2,5],[3,1,15,1],[16,1,18,1],[17,2,18,2],[1,11,1,12],[29,1,33,12],[20,5,25,5],[1,10,2,10],[20,6,25,8],[27,1,27,5],[1,1,2,1],[1,2,2,2],[1,3,2,3],[1,4,2,4],[6,6,10,8],[17,11,18,11],[17,12,18,12],[19,11,25,11],[19,12,25,12]],"flags":["formulas_cached_only"]}
[]
[null,"負担先","使途","項番","タイトル","区分","A","B","C","D","調整差異\nD - B","主な使途、成果 （厳密に一対一対応ではない）"]
[{"$nulls":6},"9/下\n実績","10/上\nRSO 入力","10/上\nRT 1次","10/上\n（2/5時点）",null,"支払先","活動内容"]
[null,"S統本","基盤整備",1,"Linux インフラ整備","包括",28.1,28.1,28.1,28.1,0,"社員・派遣","ARM、SH-4A Linux 整備 （共通費）"]
[null,null,null,2,"Linux 案件対応",null,9.3,9.3,9.3,9.3,0,"社員","一般顧客拡販対応、 Q&A 対応"]
[null,null,null,3,"Linux インフラ整備 受託移行分","受託",32,32,16,"調整中",-32,"社員・派遣","ARM、SH-4A Linux 整備 （共通費）"]
[{"$nulls":6},"右記は10上予定32.0\n内訳計画値",null,null,"予定額 9.0",null,"Magnus","AP4 電力制御、MFI ドライバー"]
[{"$nulls":9},"予定額 7.0",null,"森本","AP4 周辺ドライバー（ MIPI、BT、SPU2)"]
[{"$nulls":9},"予定額 5.0",null,"Paul","SH CPU Upstream メンテナーに加え AP4/G4 \nのメンテナーとして Upstream へのコードプッシュ"]
[{"$nulls":9},"予定額 6.0",null,"IGEL","Linux AP4/G4 標準 Linux BSP （to NEC、 RDF 等）"]
[{"$nulls":9},"5.0 (岡本さん合意額）",null,"合田","SH-NobileR 系非携帯向けLinux対応"]
[null,null,null,4,"Linux Platform整備 受託移行分",null,19.2,19.2,9.6,18,-1.1999999999999993,"社員","Ecovec ボード等設計、サポート費"]
[null,null,"案件対応",5,"S1事 Sky 顧客対応","受託",14.4,14.4,7.2,"7.2\n（期中発注 +7.2)",0,"外注","富士通テンサポート （車載 BD対応）"]
[null,null,null,6,"S1事 DTV 案件対応","受託","－",20,0,0,-20,"外注","DTV 新規案件対応"]
[null,null,null,7,"S2事 DoCoMo 統合LSI （N, P 対応）","受託","－",0,20,20,20,"社員","NEC、PMC 向け Linux サポート"]
[null,null,null,8,"S2事 Android 対応","受託",29.5,60,35,"45.8\n（内 20.0 は9/下分）",-14.2,"外注","AP4 Android 実装 （LG 他向け）\n当初計画からの費用削減分は開発計画\nの見直しで対応"]
[null,"MC統本","基盤整備",9,"Linux インフラ整備　受託移行分","受託",0,10,10,10,0,"社員・派遣","SH-4A Linux 整備 （共通費）"]
[null,null,"案件対応",10,"Rainier LinuxBSP 対応 （包括分）","包括",11.1,11.1,11.1,11.1,0,"社員","Dell、IBM 向け Linux BSP 開発、サポート"]
[null,null,null,11,"Rainier LinuxBSP 対応 （受託分）","受託",16.8,12,12,12,0]
[null,"戦略費","基盤整備",12,"SH-Linux 新機能追加","戦略費",30,30,30,"直下に振り替え","－","社員\n外注","SH kernel 開発、メインライニング\nSH gcc コンパイラメンテ\n（ Code Sourcery ）"]
[null,null,null,13,"（付替え) S１事 TV-SOC","直下受託","項番１２の全社戦略費は 10/上は\n直下費用に振り替えの指示があり\n設開本にて費用を受益者に按分\n設開本２次インプットまでに確認要",null,null,"配賦予定額 3.6",-3.6]
[null,null,null,14,"（付替え) S１事 DVD",{"$nulls":4},"配賦予定額 4.9",-4.9]
[null,null,null,15,"（付替え) S２事 モバイル１",{"$nulls":4},"配賦予定額 7.8",-7.8]
[null,null,null,16,"（付替え) S４事 CIS1",{"$nulls":4},"配賦予定額 6.9",-6.9]
[null,null,null,17,"（付替え) S４事 CIS2",{"$nulls":4},"配賦予定額 1.1",-1.1]
[null,null,null,18,"（付替え) MII 事",{"$nulls":4},"配賦予定額 5.9",-5.9]
[null,"RSO","自主開発",19,"SH-Linux 環境整備 （自主開発）",null,28,14,"RSO負担",14,0,"社員","SH-Mobile マルチメディアライブラリ開発"]
[null,"合計 （基盤整備 ＋ 案件対応）",{"$nulls":4},218.4,260.1,188.29999999999998,152.7,-77.60000000000001]
[]
[null,"- １０上 Linux 費用の中で現時点で未解決な主な項目は 項番３ （Linux インフラ整備 S統本 受託切り替え分）、項番12-18 （戦略費の直下切り替え） の２項目である。\n\n- 項番３ は９／下にはS製技がS統本全体の Linux 受益者のとりまとめを行ってくれていたが、今回は S製技は S４事分 （９／下は５．０M\\) 部分のみしか予算計上できないとの連絡。\n　 １０上については S1事（テレビ、BD関係）＋S２事 （携帯関係） の費用 （９/下では ２７．０M\\) の負担先、金額を決めて頂きたい。\n\n- 項番１２－１８ は９/上～１０／下の全社戦略費として予算化されていたものであるが、今回本件については事業との関係が直接的である（戦略的投資でない） との判断から\n　 事業部直下の費用に付替えることが求められ、現状 （設開本） にて二次インプットで表のような配分を行う予定。　本件についての事業部の了解を頂きたい。\n\n- 項番６ の 次世代DTV 向けの受託開発は、RSO 外注発注枠確保のための予算取りであり、現時点で事業部の予算と対応していなくても問題はないもの。\n- 項番１９ は RSO の赤字負担分を自主開発として処理しているもの。 １０/上は最低でも赤字額の半減を義務付けられているもの。"]

{"sheet":"SH対応","index":1,"n_rows":25,"n_cols":13,"rows_kept":25,"cut":false,"hidden":false,"merged":[[12,11,13,11],[12,12,13,12],[14,11,20,11],[14,12,20,12],[1,11,1,12],[24,1,28,12],[15,5,20,5],[1,10,2,10],[15,6,20,8],[22,1,22,5],[1,1,2,1],[1,2,2,2],[1,3,2,3],[1,4,2,4],[1,5,2,5],[3,1,10,1],[11,1,13,1],[12,2,13,2],[14,1,20,1],[14,2,20,2],[3,5,4,5],[5,5,6,5],[3,2,6,2],[7,2,10,2]],"flags":["formulas_cached_only"]}
[]
[null,"負担先","使途","項番","タイトル","区分","A","B","C","D","調整差異\nD - B","主な使途、成果 （厳密に一対一対応ではない）"]
[{"$nulls":6},"9/下\n実績","10/上\nRSO 入力","10/上\nRT 1次","10/上\n（2/5時点）",null,"支払先","活動内容"]
[null,"S統本","基盤整備",1,"Linux インフラ整備","包括",28.1,28.1,28.1,28.1,0,"社員・派遣","ARM、SH-4A Linux 整備 （共通費）"]
[null,null,null,2,"Linux 案件対応",null,9.3,9.3,9.3,9.3,0,"社員","一般顧客拡販対応、 Q&A 対応"]
[null,null,null,3,"Linux インフラ整備 受託移行分","受託",32,32,16,"調整中",-32,"社員・派遣","ARM、SH-4A Linux 整備 （共通費）"]
[null,null,null,4,"Linux Platform整備 受託移行分",null,19.2,19.2,9.6,18,-1.1999999999999993,"社員","Ecovec ボード等設計、サポート費"]
[null,null,"案件対応",5,"S1事 Sky 顧客対応","受託",14.4,14.4,7.2,"7.2\n（期中発注 +7.2)",0,"外注","富士通テンサポート （車載 BD対応）"]
[null,null,null,6,"S1事 DTV 案件対応","受託","－",20,0,0,-20,"外注","DTV 新規案件対応"]
[null,null,null,7,"S2事 DoCoMo 統合LSI （N, P 対応）","受託","－",0,20,20,20,"社員","NEC、PMC 向け Linux サポート"]
[null,null,null,8,"S2事 Android 対応","受託",29.5,60,35,"45.8\n（内 20.0 は9/下分）",-14.2,"外注","AP4 Android 実装 （LG 他向け）\n当初計画からの費用削減分は開発計画\nの見直しで対応"]
[null,"MC統本","基盤整備",9,"Linux インフラ整備　受託移行分","受託",0,10,10,10,0,"社員・派遣","SH-4A Linux 整備 （共通費）"]
[null,null,"案件対応",10,"Rainier LinuxBSP 対応 （包括分）","包括",11.1,11.1,11.1,11.1,0,"社員","Dell、IBM 向け Linux BSP 開発、サポート"]
[null,null,null,11,"Rainier LinuxBSP 対応 （受託分）","受託",16.8,12,12,12,0]
[null,"戦略費","基盤整備",12,"SH-Linux 新機能追加","戦略費",30,30,30,"直下に振り替え","－","社員\n外注","SH kernel 開発、メインライニング\nSH gcc コンパイラメンテ\n（ Code Sourcery ）"]
[null,null,null,13,"（付替え) S１事 TV-SOC","直下受託","項番１２の全社戦略費は 10/上は\n直下費用に振り替えの指示があり\n設開本にて費用を受益者に按分\n設開本２次インプットまでに確認要",null,null,"配賦予定額 3.6",-3.6]
[null,null,null,14,"（付替え) S１事 DVD",{"$nulls":4},"配賦予定額 4.9",-4.9]
[null,null,null,15,"（付替え) S２事 モバイル１",{"$nulls":4},"配賦予定額 7.8",-7.8]
[null,null,null,16,"（付替え) S４事 CIS1",{"$nulls":4},"配賦予定額 6.9",-6.9]
[null,null,null,17,"（付替え) S４事 CIS2",{"$nulls":4},"配賦予定額 1.1",-1.1]
[null,null,null,18,"（付替え) MII 事",{"$nulls":4},"配賦予定額 5.9",-5.9]
[null,"RSO","自主開発",19,"SH-Linux 環境整備 （自主開発）",null,28,14,"RSO負担",14,0,"社員","SH-Mobile マルチメディアライブラリ開発"]
[null,"合計 （基盤整備 ＋ 案件対応）",{"$nulls":4},218.4,260.1,188.29999999999998,152.7,-77.60000000000001]
[]
[null,"- １０上 Linux 費用の中で現時点で未解決な主な項目は 項番３ （Linux インフラ整備 S統本 受託切り替え分）、項番12-18 （戦略費の直下切り替え） の２項目である。\n\n- 項番３ は９／下にはS製技がS統本全体の Linux 受益者のとりまとめを行ってくれていたが、今回は S製技は S４事分 （９／下は５．０M\\) 部分のみしか予算計上できないとの連絡。\n　 １０上については S1事（テレビ、BD関係）＋S２事 （携帯関係） の費用 （９/下では ２７．０M\\) の負担先、金額を決めて頂きたい。\n\n- 項番１２－１８ は９/上～１０／下の全社戦略費として予算化されていたものであるが、今回本件については事業との関係が直接的である（戦略的投資でない） との判断から\n　 事業部直下の費用に付替えることが求められ、現状 （設開本） にて二次インプットで表のような配分を行う予定。　本件についての事業部の了解を頂きたい。\n\n- 項番６ の 次世代DTV 向けの受託開発は、RSO 外注発注枠確保のための予算取りであり、現時点で事業部の予算と対応していなくても問題はないもの。\n- 項番１９ は RSO の赤字負担分を自主開発として処理しているもの。 １０/上は最低でも赤字額の半減を義務付けられているもの。"]

{"sheet":"Sheet2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}