{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":2,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":102,"n_cols":30,"rows_kept":102,"cut":false,"hidden":false,"merged":[[83,26,84,26],[45,26,46,26],[52,26,54,26],[55,26,57,26],[62,26,63,26],[70,26,71,26],[73,26,74,26],[75,26,76,26],[79,26,80,26],[91,1,92,3],[28,1,32,3],[44,1,62,3],[28,26,30,26],[33,26,35,26],[36,26,37,26],[38,26,40,26],[47,26,48,26],[60,26,61,26],[68,26,69,26],[38,17,40,17],[33,17,35,17],[68,1,72,3],[75,1,86,3],[36,1,41,3],[33,4,35,4],[36,4,37,4],[38,4,40,4],[83,4,84,4],[83,5,84,5],[83,6,84,6],[101,18,101,19],[94,6,94,7],[99,18,99,19],[100,18,100,19],[98,18,98,19],[98,14,98,15],[99,14,99,15],[23,1,23,26],[62,6,63,7],[28,5,30,5],[33,5,35,5],[36,5,37,5],[38,5,40,5],[45,5,46,5],[47,5,48,5],[52,5,54,5],[36,17,37,17],[52,4,54,4],[52,6,54,7],[55,4,57,4],[55,6,57,7],[55,5,57,5],[45,4,46,4],[45,6,46,7],[50,6,50,7],[75,17,76,17],[62,5,63,5],[68,5,69,5],[70,5,71,5],[73,5,74,5],[68,17,69,17],[70,17,71,17],[26,12,26,16],[25,11,27,11],[47,6,48,7],[33,6,35,7],[36,6,37,7],[25,8,26,10],[31,6,31,7],[43,6,43,7],[28,6,30,7],[25,21,25,26],[26,21,26,25],[26,26,27,26],[73,17,74,17],[26,17,27,17],[25,12,25,17],[28,17,30,17],[47,17,48,17],[25,18,26,20],[60,17,61,17],[32,6,32,7],[38,6,40,7],[67,6,67,7],[64,6,64,7],[42,6,42,7],[59,6,59,7],[60,4,61,4],[66,6,66,7],[62,4,63,4],[60,5,61,5],[79,5,80,5],[73,6,74,7],[44,6,44,7],[49,6,49,7],[70,6,71,7],[58,6,58,7],[51,6,51,7],[68,6,69,7],[60,6,61,7],[65,6,65,7],[28,4,30,4],[47,4,48,4],[93,6,93,7],[91,6,91,7],[92,6,92,7],[75,7,86,7],[72,6,72,7],[79,4,80,4],[79,6,80,6],[87,7,90,7],[75,4,77,4],[75,6,77,6],[68,4,69,4],[70,4,71,4],[73,4,74,4],[75,5,77,5]],"flags":["formulas_cached_only"]}
[]
[{"$nulls":11},"　"]
[{"$nulls":11},"　"]
[{"$nulls":11},"　"]
[{"$nulls":11},"　"]
[{"$nulls":8},"超L 合計",15.599999999999998]
[{"$nulls":8},"イーゲル合計",43]
[{"$nulls":8},"アトム合計",8]
[]
[]
[]
[]
[]
[]
[null,"田中GR",null,null,0.5,null,null,"下田",1.6166666666666665,null,null,"端山",1,null,"佐久間",0.6666666666666666,null,null,"田中GR",null,0.3333333333333333,null,"下田",1.25,null,"端山",0.6666666666666666,null,"佐久間",1]
[null,"坂戸",null,null,1.1666666666666667,null,null,"吉井",1.0833333333333333,null,null,"松原",0.25,null,"濱本",0.6666666666666666,null,null,"坂戸",null,1.1666666666666667,null,"吉井",1,null,"松原",0.08333333333333333,null,"濱本",0]
[null,"田中尊",null,null,1,null,null,"岩松",1.0833333333333333,null,null,"武川",0.6666666666666666,{"$nulls":5},"田中尊",null,1,null,"岩松",1.1666666666666667,null,"武川",1]
[null,"合田",null,null,1.1833333333333333,{"$nulls":6},"工藤",1,null,"依頼研",1.5,null,null,"合田",null,1.3,{"$nulls":4},"工藤",1,null,"依頼研",1.5]
[null,"森本",null,null,0.8333333333333334,null,null,"Paul",1,null,null,"Magnus",1.0833333333333333,{"$nulls":5},"森本",null,1,null,"Paul",1,null,"Magnus",1.1666666666666667]
[{"$nulls":11},"Conrad",0.6666666666666666,null,null,null,"成果",{"$nulls":8},"Conrad",0.6666666666666666]
[]
[]
[]
[null,"RSO Linux 関連開発内容、費用分析データ (08/上実績、 ０８／下 計画）"]
[]
[{"$nulls":8},"担　当",null,null,"区　分","０８／上 活動",{"$nulls":5},"担　当",null,null,"０８／下 活動"]
[{"$nulls":12},"費用内訳",{"$nulls":4},"成果",null,null,null,"費用内訳",{"$nulls":4},"目標"]
[{"$nulls":4},"項番","区分",null,null,"担当者","月単価\nM\\/月","期総工数\n人月",null,"包括","受託","戦略","自主","合計",null,"担当者","月単価\nM\\/月","期総工数\n人月","包括","受託","戦略","自主","合計"]
[1,"［A］\nkernel 開発\n（基盤技術整備）",null,null,"A-1","共通","メインライン ＳＨ ＣＰＵ 対応",null,"Paul",1.8,6,"外注（RTA）",null,null,null,10.8,10.8,"- kernel 進化への追従 （3か月毎に更新）\n- SuperH CPU アーキテクチャ対応 （ SH-2A、SH-4A-X2)\n- レファレンスプラットフォーム対応 （Native Code 対応）","Paul",1.8,6,null,null,null,10.8,10.8,"- kernel 進化への追従 （3か月毎に更新）\n- SuperH CPU アーキテクチャ対応 （ SH-4A-X3, パワマネ)\n- レファレンスプラットフォーム対応 （Native Code 対応）"]
[2,{"$nulls":7},"岩松",1.2,1.5,"派遣(超L)",1.7999999999999998,null,null,null,1.7999999999999998,null,"岩松",1.2,1,1.2,null,null,null,1.2]
[3,{"$nulls":7},"Magnus",1.7,4,"外注（iGel)",null,null,null,6.8,6.8,null,"Magnus",1.7,6,null,null,null,10.2,10.2]
[4,null,null,null,"A-2","共通","ｕｂｏｏｔ ＳＨ 対応",null,"岩松",1.2,1,"派遣（超Ｌ）",1.2,null,null,null,1.2,"世界標準ブートローダーのメンテナンス、新規対応","岩松",1.2,0.5,0.6,null,null,null,0.6,"世界標準ブートローダーのメンテナンス、新規対応"]
[5,null,null,null,"A-3","S１事","ルネサス USB 対応",null,"下田",1,1,"プロパー（出向受）",1,null,null,null,1,"M66596/597, M66291 ドライバーメインライニング、保守","下田",1.11,1,1.11,null,null,null,1.11,"M66596/597, M66291 ドライバーメインライニング、保守"]
[6,null,null,"比率","A-4","共通","kernel 自動テスト環境",null,"岩松",1.2,0.5,"派遣（超Ｌ）",0.6,null,null,null,0.6,"- kernel 品質確保 （リグレッションテスト）\n- kernel ベンチマーク → SH 最適化\n- 顧客に対する ルネサス取組みアピール","田中GR",1.11,1,1.11,null,null,null,1.11,"- kernel 品質確保 （リグレッションテスト）\n- kernel ベンチマーク → SH 最適化\n- Userland (Gentoo) への品質情報フィードバック"]
[7,"8/上 ＝",28.800000000000004,0.1771293967144956,{"$nulls":4},"下田",1.2,0.5,"プロパー（出向受）",0.6,null,null,null,0.6,null,"　",{"$nulls":6},0]
[8,"8/下 ＝",31.02,0.1949802945447003,{"$nulls":4},"工藤",1,6,"外注(iGel)",6,null,null,null,6,null,"工藤",1,6,6,null,null,null,6]
[9,"［B］\n先行技術開発\n（ルネサス差別化技術）",null,null,"B-1","S１、S2","Linux MMF (→ SH-Mobile 全般 ）",null,"Conrad",1.5,4,"外注（イーゲル）",null,null,null,6,6,"- Sシ括 VPU コアミドルウエア対応\n- MIGO-R BSP への ミドルウエア組み込み評価","Conrad",1.5,4,null,null,null,6,6,"- OpenMAX/IL(Bellagio) 実装、ロゴ取得\n- Media connection-manager の開発、実装"]
[10,{"$nulls":7},"端山",2,1,"外注（イーゲル）",null,null,null,2,2,null,"端山",2,1,null,2,null,null,2]
[11,null,null,null,"B-2","S1,S2","DirectFB （→ Sky、Blues、LiMO 他）",null,"端山",2,5,"外注（イーゲル）",null,10,null,null,10,"- DTV-H、Sky、Blues の2DG 対応専用ドライバー開発、最適化\n- SH-MobileR2 対応コード開発、一般公開\n- 次世代 MMF 連携 （DirectFB2.0)","佐久間",1,6,null,null,null,6,6,"- Blues に向けた 2DG 描画性能の最適化\n- DirectFB 2.0 試行による Codec と Graphics の統合\n- LiMO Spec の MobileG シリーズへの実証"]
[12,{"$nulls":7},"田中尊",1.11,2,"プロパー"," ",2.22,null,null,2.22,null,"田中尊",1.11,2," ",2.22,null,null,2.22]
[13,{"$nulls":7},"佐久間",1,4,"外注（アトム）",null,null,null,4,4,null,"端山",2,3,null,4," ",2,6]
[14,null,null,null,"B-3","共通","SH-SMP シミュレーション技術 QEMU",null,"依頼研",1,3,"スポット依頼研（外注扱い）",null,null,3,null,3,"次世代マルチコア開発環境、ST連携 → CPU開 と協調","依頼研",1,3," ",null,3,null,3,"- Ｂｌｕｅｓ 性能解析,最適化への適用予定"]
[15,"8/上 ＝",43.54,0.26778520600517836,"B-4","S統本","SH-Java (→ BD-J for Sky、Blues)",null,"依頼研",2.35,6,"依頼研 (中研）",14.1,null,null,null,14.100000000000001,"Sky 性能課題解析 → Blues アーキテクチャ設計に反映","依頼研",2.35,6,14.1,null,null,null,14.100000000000001,"- Blues 向け BD-Java 最適実装、性能解析"]
[16,"8/下 ＝",41.72,0.2622365534624403,"B-5","S１事","情報家電ソフトウエアプラットフォーム（→DTV)",null,"田中GR",1.11,2,"プロパー",2.22,null,null,null,2.22,"経産省プロジェクト、次世代 DTV ソフトウエア標準化","武川",1.2,2,null,null,null,2.4,2.4,"- Phase1 実証実験 （3月リリース義務付け）"]
[17,"［C］\nBSP 開発\n（拡版支援）",null,null,"C-1",null,"SH7203　（RSK7203)",null,"吉井",1.2,1,"派遣（超Ｌ）",1.2,null,null,null,1.2,"SH2A-noFPU向けGNU toolchain整備","吉井",1.2,0.5,0.6,null,null,null,0.6,"- SH-2A 向け環境（kernel。toolchain) 整備"]
[18,null,null,null,"C-2","S４事","MX-G （SH-2A)",null,"下田",1.11,1,"プロパー（出向受）",1.11,null,null,null,1.11,"SH2A向けLinux kernel(nonMMU対応)の整備、MX-Gドライバ開発","森本",1.11,2,2.22,null,null,null,2.22,"- MX-G デモシステム開発 （ドライバー整備、デモアプリ実装）\n- MX-G Type2 実装評価ボードむけ検証作業"]
[19,{"$nulls":7},"吉井",1.2,2,"派遣（超Ｌ）",2.4,null,null,null,2.4,"SH2A-noFPU向けGNU toolchain整備（uClibcメンテナンス）","吉井",1.2,2,2.4,null,null,null,2.4]
[20,null,null,null,"C-3",null,"SH7721 SE",null,"岩松",1.2,0.5,"派遣（超Ｌ）",0.6,null,null,null,0.6,"u-boot(kernel bootloader）の整備、各種デバイスドライバ（LCDC,USBH,USBF,SIM,SDHI）開発","岩松",1.2,0.5,0.6,null,null,null,0.6,"- RTE　向け BSP 保守、 Q&A 対応\n- EPSON （Keystream WLAN) 向け BSP 提供"]
[21,{"$nulls":7},"森本",1.11,2,"プロパー",2.22,null,null,null,2.22,null,"森本",1.11,0,0,null,null,null,0]
[22,null,null,null,"C-4","S４事","SH7763  （◎ SH7763RDP）",null,"岩松",1.2,2,"派遣（超Ｌ）",2.4,null,null,null,2.4,"SH7763RDPボード向けu-bootならびにkernelの更新・メンテナンス","岩松",1.2,1.5,1.7999999999999998,null,null,null,1.7999999999999998,"- RTE　向け BSP 保守、 Q&A 対応"]
[23,null,null,null,"C-5","S４事","SH7751R （◎ R2D+)",null,"岩松",1.2,1,"派遣（超L)",1.2,null,null,null,1.2,"R2D+ボード向けu-bootならびにkernelの更新・メンテナンス","岩松",1.2,0.5,0.6,null,null,null,0.6,"- ルネサス標準BSP 保守"]
[24,null,null,null,"C-6","S2事","SH7366 （SH-MobileUL2)",null,"合田",1.11,0.5,"プロパー",0.555,null,null,null,0.555,"SH7366ボード向けu-bootならびにkernelの整備","森本",1.11,1,1.11,null,null,null,1.11,"- RTE、RTA、韓国顧客向け BSP 環境整備"]
[25,null,null,null,"C-7","S2事","SH7722　（◎　MIGO-R）",null,"Magnus",1.8,1.5,"外注（イーゲル）",null,null,null,2.7,2.7,"SH7722 Migo-Rボード向け各種デバイスドライバのメンテナンス","Magnus",1.7,0.5,null,null,null,0.85,0.85,"- RTE Tier１ 顧客向け BSP サポート、 Q&A 対応\n- RTA 向け 拡販支援活動 （デモアプリの実装　など）\n- アイホン向け BSP サポート、 Q&A 対応"]
[26,{"$nulls":7},"合田",1.11,2,"プロパー",2.22,null,null,null,2.22,"Migo-Rボード向け各種デバイスドライバの単体テスト、VPUミドル評価","合田",1.11,1.5,1.665,null,null,null,1.665]
[27,{"$nulls":7},"田中尊",1.11,2,"プロパー",2.22,null,null,null,2.22,"Migo-Rボード向けDirectFB評価、単体テスト","田中尊",1.11,1,1.11,null,null,null,1.11]
[28,null,null,null,"C-8","S2事","SH7723　（◎　ALGO AP320）",null,"Magnus",1.7,1,"外注（イーゲル）",null,null,null,1.7,1.7,"SH7723 AP-320ボード向け各種デバイスドライバのメンテナンス","Magnus",1.7,0.5,null,null,null,0.85,0.85,"- RTE Tier1 顧客向け BSP サポート、 Q&A 対応、 BSP 拡張\n- DNP、京セラ など国内顧客むけ BSP サポート、拡販支援活動\n- MMF 実装、OpenMAX/IL ロゴ取得活動"]
[29,{"$nulls":7},"合田",1.11,2,"プロパー",2.22,null,null,null,2.22,"AP-320ボード向け各種デバイスドライバの単体テスト、VPUミドル評価","合田",1.11,2,2.22,null,null,null,2.22]
[30,{"$nulls":7},"田中尊",1.11,1.5,"プロパー",1.665,null,null,null,1.665,"AP-320ボード向けDirectFB評価、単体テスト","田中尊",1.11,1,1.11,null,null,null,1.11]
[31,null,null,null,"C-9","S2事","SH7723　Diamond Head",null,"森本",1.11,3,"プロパー",3.33,null,null,null,3.33,"(RTA)Diamond Headボード向けLinuxBSP整備","森本",1.11,2,2.22,null,null,null,2.22,"- RTA 向け BSP Snapshot 提供"]
[32,null,null,null,"C-10","S４事","SH778０ （◎　HL）",null,"下田",1.11,0.5,"プロパー（出向受）",0.555,null,null,null,0.555,"SH7780HLボード向けkernelメンテナンス","森本",1.11,1,1.11,null,null,null,1.11,"- SH-X2 ルネサス標準BSP 保守"]
[33,null,null,null,"C-11","S４事","SH7785　（◎　LCR）",{"$nulls":9},0,"R0P7785LC001RLボード向けkernelメンテナンス","下田",1.11,2,2.22,null,null,null,2.22,"- RTE 向け BSP サポート、 Q&A 対応\n- 国内、海外向け SH7785 拡販支援活動"]
[34,{"$nulls":7},"下田",1.11,1.5,"プロパー（出向受）",1.665,null,null,null,1.665,null,"岩松",1.2,1.5,1.7999999999999998,null,null,null,1.7999999999999998]
[35,null,null,null,"C-12","S４事\n（S1事）","SH7786 （ボード調整中）\n　→ Blues SDK 先行開発",{"$nulls":9},0,null,"下田",1.11,1,1.11,null,null,null,1.11,"- BLUES 向け Linux-SMP 先行実装、評価\n- デバイスドライバーの整合性検証、ドライバーの改修"]
[36,"8/上 ＝",35.73199999999999,0.21976345845147063,{"$nulls":12},0,null,"岩松",1.2,1.5,1.7999999999999998,null,null,null,1.7999999999999998]
[37,"8/下 ＝",31.279999999999994,0.1966145587800846,"C-13","S１事","HL-DTVH （→ 情報家電PF、UWB）",null,"下田",1.11,0.7,"プロパー（出向受）",0.777,0.777,null,null,0.777,"HL-DTVH向けkernelアップデート、ドライバ整備","下田",1.11,1,1.11,null,null,null,1.11,"- B-5 向け BSP 提供、 DTV-H Tuner 拡張部分のドライバー対応"]
[38,null,null,null,"C-14","S2事","G2 Android （EVM)",null,"下田",1.11,2,"プロパー（出向受）",2.22,2.22,null,null,2.22,"G2向けAndroidデモ環境整備","下田",1.11,0,0,null,null,null,0]
[39,null,null,null,"C-15","S2事","G2 ALP （EVM)",null,"下田",1.11,2.5,"プロパー（出向受）",2.7750000000000004,null,null,null,2.7750000000000004,"G2向けAndroidデモ環境整備","下田",1.11,0.5,0.555,null,null,null,0.555,"- G3 への ALP 実装"]
[40,null,null,null,"C-16","S2事","G3 LiMO （EVM)",null,"　",null,null,"　",{"$nulls":4},0,null,"下田",1.11,2,2.22,null,null,null,2.22,"- LiMO ソースコードの管理、 G3 への実装、検証"]
[41,"［D］\nToolchain 開発\n（基盤技術整備）",null,null,"D-1","共通","KPIT 対応",null,"吉井",1.2,1,"派遣（超Ｌ）",1.2,null,null,null,1.2,"KPITリリースv802 sh-linux向けgcc/glibcの仕様確認ならびに品質向上サポート、検収評価作業","吉井",1.2,0.5,0.6,null,null,null,0.6,"- KPIT V802 リリース支援　（仕様作成、中間成果物検証、最終検証 ）"]
[42,{"$nulls":7},"坂戸",1.11,1,"プロパー",1.11,null,null,null,1.11,null,"坂戸",1.11,0.5,0.555,null,null,null,0.555]
[43,null,null,null,"D-2","共通","ELF-fdpic （→SH-2A、MX-G）",null,"CodeSourcery",2.1,0,"外注（RTA 経由）",{"$nulls":4},0,"SH2A(nonMMUアーキテクチャ)向けuclibcメンテナンス、検収評価作業","CodeSourcery",2.1,0,{"$nulls":4},0,"　"]
[44,{"$nulls":7},"Paul",2,0,"外注（RTA 経由）",{"$nulls":4},0,null,"Paul",2,0,{"$nulls":4},0]
[45,null,null,null,"D-3","共通","Gentoo Userland 整備",null,"吉井",1.2,2,"派遣（超Ｌ）",2.4,null,null,null,2.4,"gentoo comuniteeメインラインへのSH archサポート活動","吉井",1.2,2,2.4,null,null,null,2.4,"- Gentoo SH 資産整備支援 （experimental → Stable 化を目指す）"]
[46,"8/上 ＝",30.510000000000005,0.18764645464441876,"D-4","共通","CodeSouery G++ Lite",null,"CodeSourcery",2.1,12,"外注（RTA 経由）",null,null,25.200000000000003,null,25.200000000000003,"SH4A向けLinux toolchainメンテナンスならびに整備支援","CodeSourcery",2.1,12,null,null,25.200000000000003,null,25.200000000000003,"- CodeSourcery G++ Lite 開発支援、開発成果検証"]
[47,"8/下 ＝",29.955000000000002,0.1882860968112991,{"$nulls":4},"吉井",1.2,0.5,"派遣（超Ｌ）",0.6,null,null,null,0.6,null,"吉井",1.2,1,1.2,null,null,null,1.2]
[48,"［E］\n顧客案件サポート",null,null,"E-1","S1事","Pioneer Sky","国内案件","坂戸",1.11,4,"プロパー",null,4.44,null,null,4.44,"sky向けLinuxBSPメンテナンス、Linux一般コンサルティングサポート","坂戸",1.11,1.5,null,1.665,null,null,1.665,"sky向けLinuxBSPメンテナンス、Linux一般コンサルティングサポート"]
[49,{"$nulls":7},"武川",1.2,4,"外注（イーゲル）",null,"　",null,4.8,4.8,null,"武川",1.2,1,null,1.2,null," ",1.2]
[50,{"$nulls":7},"濱本",1,4,"外注（アトム）"," ",4,null,null,4,"sky向けLinux不具合対応ならびに品質向上サポート","濱本",4,1,"  ",4,null,null,4,"sky向けLinux不具合対応ならびに品質向上サポート"]
[51,null,null,null,"E-2","S1事","富士通テン Sky",null,"坂戸",1.11,1,"プロパー",null,1.11,null,null,1.11,"sky向けLinuxBSPメンテナンス、Linux一般コンサルティングサポート","坂戸",1.11,2,null,2.22,null,null,2.22,"sky向けLinuxBSPメンテナンス、Linux一般コンサルティングサポート"]
[52,null,null,null,"E-3","S1事","Pioneer Blues",{"$nulls":9},0,null,"武川",1.2,3,null,3.6,null," ",3.5999999999999996,"Blues 向け Linux BSP 1st リリース提供 （SMP 非対応）\nSMP 有効活用のための顧客ガイダンスの実施"]
[53,{"$nulls":7},"坂戸",1.11,0,"プロパー",null,0,null,null,0,null,"坂戸",1.11,2,null,2.22,null,null,2.22]
[54,null,null,null,"E-4","S1事","バッファロー　DTV-H",null,"坂戸",1.11,1,"プロパー",null,1.11,null,null,1.11,"DTV-H向けカーネルNANDブート対応等、顧客対応","坂戸",1.11,1,null,1.11,null,null,1.11,"顧客開発支援 （ドライバー改造、Linux 一般対応 ）"]
[55,null,null,null,"E-5","S2事","アイホン SH-MobileR",null,"合田",1.11,1,"プロパー",null,1.11,null,null,1.11,"アイホン向けVPUミドルウェアデモ環境の構築","合田",1.11,1.5,null,1.665,null,null,1.665,"VPU、CEU ミドルウエア導入支援、 MIGO-BSP 拡張サポート"]
[56,null,null,null,"E-6","S2事","DNP SH-MobileR2",null,"三宅",1,1,"外注(LineoSolutions)",null,null,null,1,1,"SH7723 向けLinuxBSP整備支援",{"$nulls":8},"DNP 向け Linux BSP 提供\n監視カメラ仕様提案 → 差別化機能の先行実装"]
[57,{"$nulls":7},"田中尊",1.11,0.2,"プロパー",null,0.22200000000000003,null,null,0.22200000000000003,"SH7723向けDirectFBデモ環境整備","田中尊",1.11,1.5,null,1.665,null,null,1.665]
[58,{"$nulls":15},0,{"$nulls":8},0]
[59,{"$nulls":15},0,{"$nulls":8},0]
[60,"8/上 ＝",19.235,0.11830152589594868,"E-7","S2、S4","RTE MIGO-R","海外案件","合田",1.11,1,"プロパー",null,1.11,null,null,1.11,"RTEリクエストによるMigo-Rボード向けLinuxBSP環境整備","合田",1.11,2,2.22,null,null,null,2.22,"RTEリクエストによるMigo-Rボード向けLinuxBSP環境整備"]
[61,"8/下 ＝",22.119999999999997,0.13903817264115959,"E-8","S2、S4","RTA MIGO-R",null,"合田",1.11,0.3,"プロパー",null,0.333,null,null,0.333,"RTAリクエストによるMigo-Rボード向けLinuxBSP環境整備","合田",1.11,0.5,null,0.555,null,null,0.555,"RTAリクエストによるMigo-Rボード向けLinuxBSP環境整備"]
[62,{"$nulls":15},0,{"$nulls":8},0]
[63,{"$nulls":15},0,{"$nulls":8},0]
[64,"［F］\nその他",null,null,"F-1","共通","CE Linux Forum 対応",null,"松原",2,1.5,"プロパー",null,null,null,3,3,"リアルタイム性能向上への取組み（RT-PREEMPT機能の実現）","松原",2,0.5,null,null,null,1,1,"リアルタイム性能向上への取組み（RT-PREEMPT機能の実現）"]
[65,null,null,null,"F-2","共通","日本OSS 推進フォーラム対応",null,"田中GR",1.11,1,"プロパー",1.11,null,null,null,1.11,"組込み分野に於けるOSS利用促進普及活動推進","田中GR",1.11,1,1.11," ",null,null,1.11,"組込み分野に於けるOSS利用促進普及活動推進"]
[66,"8/上 ＝",4.776000000000001,0.029373958288487184,"F-3","共通","中国大学 Linux 普及支援活動",null,"合田",1.11,0.3,"プロパー",0.333," ",null,null,0.333,"SH7709向けLinuxBSP開発支援","合田",1.11,0.3,0.333," ",null,null,0.333,"SH7709向けLinuxBSP開発支援"]
[67,"8/下 ＝",2.9980000000000007,0.018844323760316303,"F-4","S2事","SH-Mobile コンソーシアム対応",null,"田中尊",1.11,0.3,"プロパー",0.333," ",null,null,0.333,"SH7723向けLinuxBSP環境整備(Vmwearイメージ作成)","田中尊",1.11,0.5,0.555," ",null,null,0.555,"SH7723向けLinuxBSP環境整備 (OpenMAX/IL 抽象化支援）"]
[]
[{"$nulls":11},"　　",65.93799999999999,28.651999999999997,28.200000000000003,42.800000000000004,162.59300000000013,{"$nulls":4},62.67299999999998,28.119999999999997,28.200000000000003,40.1,159.09299999999996]
[]
[{"$nulls":14},"　",null,"　",null,null,null,"S統本","MC統本","合計",null,"共通",15.107999999999999,"(24%)"]
[{"$nulls":14},"　",null,"　",null,"Linux インフラ整備",null,42.4,10.6,53,null,"S統本",47.56499999999998,"(76%)"]
[{"$nulls":18},"Linux 案件対応",null,8.2,2,10.2]
[{"$nulls":20},50.599999999999994,12.6,63.2]

{"sheet":"Sheet2","index":1,"n_rows":24,"n_cols":5,"rows_kept":24,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[null,null,"単価","工数","金額"]
[null,"田中GR",null,{"$error":"#NAME?"}]
[null,"坂戸"]
[null,"田中尊"]
[null,"合田"]
[null,"森本"]
[]
[null,"下田"]
[null,"吉井"]
[null,"岩松"]
[]
[null,"Paul"]
[]
[null,"端山"]
[null,"松原"]
[null,"武川"]
[null,"工藤"]
[null,"Magnus"]
[null,"Conrad"]
[]
[null,"佐久間"]
[null,"濱本"]
[]
[null,"依頼研"]

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}